## ABHEES_INTERIOR
Bug ID | Module Name | Bug Description | Step to Reproduce | Priority | Severity | Reported By | Reported Date | Status
Abhees_001 | Home Page | Grammer issue in the banner text | Open home page and read the banner content | Low | Low | Johns George | 2025-05-15 | new
Abhees_002 | Home Page | Logo not clickable to Home Button, it is not respond | Open the home page and Click on the button of "Home" | High | Medium | Johns George | 2025-05-15 | new
Abhees_003 | Home Page | Logo not clickable to About Button, it is not respond | Open the home page and Click on the button of "About" | Medium | Medium | Johns George | 2025-05-15 | new
Abhees_004 | Home Page | Logo not clickable to Contact Button, it is not respond | Open the home page and Click on the button of "Contact" | Medium | Medium | Johns George | 2025-05-15 | new
Abhees_005 | Header & Footer | facebook icon not linked correctly. | Scroll to header & footer and click on facebook icon; observe it as broken link. | Medium | Low | Johns George | 2025-05-15 | new
Abhees_006 | Header & Footer | Twitter icon not linked correctly. | Scroll to header & footer and click on twitter icon; observe it as broken link. | Medium | Low | Johns George | 2025-05-15 | new
Abhees_007 | Header & Footer | Linkedin icon not linked correctly. | Scroll to header & footer and click on linkedin icon; observe it as broken link. | Medium | Low | Johns George | 2025-05-15 | new
Abhees_008 | Header & Footer | Instagram icon not linked correctly. | Scroll to header & footer and click on Instagram icon; observe it as broken link. | Medium | Low | Johns George | 2025-05-15 | new
Abhees_009 | Header | Youtube icon not linked correctly. | Scroll to header and click on Youtube icon; observe it as broken link. | Medium | Low | Johns George | 2025-05-15 | new
Abhees_010 | Navigation Menu | Navigation links are not keyboard accessible, hindering usability. | Use Tab key to navigate through the menu; observe lack of focus indicators. | High | High | Johns George | 2025-05-15 | new
Abhees_011 | Contact Form | No validation for email field allows submission of invalid email addresses. | Submit the contact form with an invalid email format; form accepts submission. | High | High | Johns George | 2025-05-15 | new
Abhees_012 | Page Titles | Multiple pages have identical titles, | Navigate to different pages and observe the browser tab titles. | Medium | Medium | Johns George | 2025-05-15 | new
Abhees_013 | Image Optimization | Images are not optimized, leading to slow load times. | Analyze images using performance tools; observe large file sizes. | Medium | Medium | Johns George | 2025-05-15 | new
Abhees_014 | Color Contrast | Some text lacks sufficient contrast against background. | Use accessibility tools to check color contrast ratios. | Medium | Medium | Johns George | 2025-05-14 | new
Abhees_015 | Page Layout | Extra white space at bottom of some pages | Scroll down and observe extra spacing | Low | Low | Johns George | 2025-05-14 | new
Abhees_016
Abhees_017
Abhees_018
Abhees_019
Abhees_020